## Maintenances
The duration of the maintenance work(s) listed here is estimated on today´s basis. An exact schedule will only evolve during the maintenance work(s). No responsibility is taken for the correctness of the data and exclusions of liability of Fluxys Deutschland GmbH apply here | [6 empty] | Last update: 19/07/2022 14:59
Affected Point | Start | End | Duration (Days) | Work number | Reduction with regard to technical capacity | Work description | Additional information
Greifswald Entry | 2022-05-16 06:00 | 2022-05-25 06:00 | 9 | 21 | 1.393.729 kWh/h (20,4%)* | Reduction due to maintenance operations in OGE Network. Affected Point: MAP Achim II | * Of which: DZK1: 0 kWh/h DZK2: 1.393.729 kWh/h
Greifswald Entry | 2022-07-12 06:00 | 2022-07-22 06:00 | 10 | 1 | 100% | Shutdown due to maintenance operations Landfallstation Greifswald
Greifswald Entry | 2022-07-11 06:00 | 2022-07-21 06:00 | 10 | 1 | 100% | Shutdown due to maintenance operations Landfallstation Greifswald | New duration
Greifswald Entry | 2022-07-12 06:00 | 2022-07-13 06:00 | 1 | 3 | 33% | Reduction due to maintenance operations Landfallstation Greifswald | from 8:00 a.m. until 6:00 p.m. flow is reduced to 0
Greifswald Entry | 2022-07-13 06:00 | 2022-07-14 06:00 | 1 | 4 | 33% | Reduction due to maintenance operations Landfallstation Greifswald | from 8:00 a.m. until 6:00 p.m. flow is reduced to 0
Lubmin II Entry | 2022-07-26 06:00 | 2022-07-31 06:00 | 5 | 16 | 100% | Shutdown due to maintenance operations Landfallstation Lubmin II
Lubmin II Entry | 2022-07-26 06:00 | 2022-08-05 06:00 | 10 | 16 | 100% | Shutdown due to maintenance operations Landfallstation Lubmin II | Maintenance prolongation
Lubmin II Entry | 2022-07-21 06:00 | 2022-08-01 06:00 | 11 | 16 | 100% | Shutdown due to maintenance operations Landfallstation Lubmin II | New maintenance period
Lubmin II Entry | 2022-07-21 06:00 | 2022-08-01 06:00 | 11 | 16 | 100% | Shutdown due to maintenance operations Landfallstation Lubmin II | Cancelled
Lubmin II Entry | 2022-07-26 06:00 | 2022-07-30 06:00 | 4 | 17 | 46% | Reduction due to maintenance operations on the pipeline | Max.:39.375.000 kWh/h
Lubmin II Entry | 2022-07-26 06:00 | 2022-07-30 06:00 | 4 | 17 | 45% | Reduction due to maintenance operations on the pipeline
Deutschneudorf EUGAL | 2022-07-26 06:00 | 2022-07-30 06:00 | 4 | 18 | 6% | Reduction due to maintenance operations on the pipeline | Max.:39.375.000 kWh/h
Deutschneudorf EUGAL | 2022-07-26 06:00 | 2022-07-30 06:00 | 4 | 18 | 5% | Reduction due to maintenance operations on the pipeline
Deutschneudorf EUGAL | 2022-07-26 06:00 | 2022-07-31 06:00 | 5 | 20 | 46% | Reduction due to maintenance operations on the pipeline | Max.:22.500.000 kWh/h
Deutschneudorf EUGAL | 2022-07-26 06:00 | 2022-08-05 06:00 | 10 | 20 | 46% | Reduction due to maintenance operations on the pipeline | Max.:22.500.000 kWh/h Maintenance prolongation
Deutschneudorf EUGAL | 2022-07-21 06:00 | 2022-08-01 06:00 | 11 | 20 | 46% | Reduction due to maintenance operations on the pipeline | Max.:22.500.000 kWh/h New maintenance period
Deutschneudorf EUGAL | 2022-07-21 06:00 | 2022-08-01 06:00 | 11 | 20 | 46% | Reduction due to maintenance operations on the pipeline | Cancelled
Greifswald Entry | 2022-08-29 06:00 | 2022-09-20 06:00 | 21 | 22 | 20.4% | Reduction due to maintenance operations in OGE Network. | DZK2