## Maintenances
The duration of the maintenance work(s) listed here is estimated on today´s basis. An exact schedule will only evolve during the maintenance work(s). No responsibility is taken for the correctness of the data and exclusions of liability of Fluxys Deutschland GmbH apply here | [6 empty] | Last update: 12/10/2021 17:55
Affected Point | Start | End | Duration (Days) | Work number | Reduction with regard to technical capacity | Work description | Additional information
Greifswald Entry | 2021-07-13 06:00 | 2021-07-23 06:00 | 10 | 1 | 100% | Shutdown due to maintenance operations Landfallstation Greifswald
Greifswald Entry | 2021-07-21 06:00 | 2021-07-22 06:00 | 1 | 2 | 42% | Reduction due to maintenance operations Landfallstation Greifswald | from 8:00 a.m. until 6:00 p.m. flow is reduced to 0
Greifswald Entry | 2021-07-22 06:00 | 2021-07-23 06:00 | 1 | 3 | 42% | Reduction due to maintenance operations Landfallstation Greifswald | from 8:00 a.m. until 6:00 p.m. flow is reduced to 0
Greifswald Entry | 2021-08-30 06:00 | 2021-09-13 06:00 | 14 | 4 | 48% | Reduction due to maintenance operations Landfallstation Greifswald
Lubmin II Entry | 2021-07-13 06:00 | 2021-07-17 06:00 | 4 | 4 | 100% | Shutdown due to maintenance operations Landfallstation Greifswald
Greifswald Entry | 2021-10-01 06:00 | 2021-10-09 06:00 | 8 | 5 | 1.393.729 kWh/h (20,4%)* | Reduction due to maintenance operations in OGE Network. Affected Point: MAP Achim II | * Of which: DZK1: 0 kWh/h DZK2: 1.393.729 kWh/h