## Maintenances
Last Update: 23/11/2018 15:03:38
Affected Point | Start | End | Duration (Days) | Reduction of the TAC due to the maintenance | possible impact on firm bookings | Work | Affected pipeline or network | Work No. | Status | Additional information
Wallbach Exit | 2018-01-01 06:00 | 2018-04-01 06:00 | 91 | 6.967.379* kWh/h 45,6 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: FAC = 1.915.273 kWh/h RAC = 5.052.106 kWh/h
Bocholtz Entry | 2018-01-01 06:00 | 2018-04-01 06:00 | 91 | 2.327.983* kWh/h 15,2 % | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: cFAC = 1.868.595 kWh/h RAC = 459.388 kWh/h
Bocholtz Entry | 2018-03-19 06:00 | 2018-03-23 06:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | modified
Wallbach Exit | 2018-03-19 06:00 | 2018-03-23 06:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | modified
Bocholtz Entry | 2018-03-19 06:00 | 2018-03-24 06:00 | 6 | 2.659.950* kWh/h 17,4 % | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | postponed | * only cFAC is affected
Wallbach Exit | 2018-03-19 06:00 | 2018-03-24 06:00 | 6 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | postponed | There is no impact on the current firm technical available capacity at the IP Wallbach.
Wallbach Exit | 2018-04-01 06:00 | 2018-10-01 06:00 | 184 | 7.597.029* kWh/h 49,7 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: FAC = 2.544.923 kWh/h RAC = 5.052.106 kWh/h
Bocholtz Entry | 2018-04-01 06:00 | 2018-10-01 06:00 | 184 | 2.469.333* kWh/h 16,1% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: cFAC = 1.868.595 kWh/h RAC = 600.738 kWh/h
Bocholtz Entry | 2018-05-14 08:00 | 2018-05-18 16:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | postponed
Wallbach Exit | 2018-05-14 08:00 | 2018-05-18 16:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | postponed
Bocholtz Entry | 2018-05-22 06:00 | 2018-05-26 06:00 | 5 | 2.184.500* kWh/h 14,3% | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | terminated | * only cFAC is affected
Wallbach Exit | 2018-05-22 06:00 | 2018-05-26 06:00 | 5 | 829.339* kWh/h 5,4 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019651 | terminated | * only FAC is affected
Bocholtz Entry | 2018-06-19 06:00 | 2018-06-20 18:00 | 2 | k.A | currently not foreseeable | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21019664 | postponed
Wallbach Exit | 2018-06-19 06:00 | 2018-06-20 18:00 | 2 | k.A | currently not foreseeable | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21019664 | postponed
Bocholtz Entry | 2018-06-25 08:00 | 2018-06-29 16:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019657 | postponed
Wallbach Exit | 2018-06-25 08:00 | 2018-06-29 16:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019657 | postponed
Bocholtz Entry | 2018-06-25 08:00 | 2018-06-29 16:00 | 5 | 1.397.502* kWh/h 9,1% | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019657 | canceled | * only RAC is affected
Wallbach Exit | 2018-06-25 08:00 | 2018-06-29 16:00 | 5 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019657 | canceled | There is no additional impact on the current firm technical available capacity at the IP Wallbach
Bocholtz Entry | 2018-07-01 06:00 | 2018-07-06 18:00 | 6 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019648 | modified
Wallbach Exit | 2018-07-01 06:00 | 2018-07-06 18:00 | 6 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019648 | modified
Wallbach Exit | 2018-07-01 06:00 | 2018-07-07 06:00 | 7 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019648 | terminated | There is no additional impact on the current firm technical available capacity at the IP Wallbach
Bocholtz Entry | 2018-07-01 06:00 | 2018-07-07 06:00 | 7 | 4.561.750* kWh/h 29,8% | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019648 | terminated | * only RAC is affected
Bocholtz Entry | 2018-07-09 08:00 | 2018-07-20 16:00 | 12 | k.A | currently not foreseeable | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | OGE-Network | 21018696 | modified
Wallbach Exit | 2018-07-09 08:00 | 2018-07-20 16:00 | 12 | k.A | currently not foreseeable | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | OGE-Network | 21018696 | modified
Bocholtz Entry | 2018-07-09 08:00 | 2018-07-20 16:00 | 12 | 0 | yes | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | OGE-Network | 21018696 | modified | The exact amount of capacity reduction will be communicated soon
Wallbach Exit | 2018-07-09 08:00 | 2018-07-20 16:00 | 12 | 0 | yes | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | OGE-Network | 21018696 | modified | The exact amount of capacity reduction will be communicated soon
Bocholtz Entry | 2018-07-09 08:00 | 2018-07-14 06:00 | 5 | 5.301.130* kWh/h 34,6% | yes | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | OGE-Network | 21018696 | terminated | * only cFAC is affected
Wallbach Exit | 2018-07-09 08:00 | 2018-07-14 06:00 | 5 | 5.154.513* kWh/h 33,7% | yes | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | OGE-Network | 21018696 | terminated
Bocholtz Entry | 2018-07-23 06:00 | 2018-07-27 18:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020076 | modified
Wallbach Exit | 2018-07-23 06:00 | 2018-07-27 18:00 | 5 | k.A | currently not foreseeable | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020076 | modified
Bocholtz Entry | 2018-07-23 06:00 | 2018-08-04 06:00 | 13 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020076 | terminated
Wallbach Exit | 2018-07-23 06:00 | 2018-08-04 06:00 | 13 | 686.191* kWh/h 4,5% | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020076 | terminated | * only FAC is affected
Bocholtz Entry | 2018-08-06 08:00 | 2018-08-11 06:00 | 5 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019662 | terminated
Wallbach Exit | 2018-08-06 08:00 | 2018-08-11 06:00 | 5 | 2.975.096* kWh/h 19,4% | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019662 | terminated | *of which: FAC = 2.727.202 kWh/h RAC = 247.894 kWh/h
Bocholtz Entry | 2018-08-13 08:00 | 2018-08-17 16:00 | 5 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019663 | modified
Wallbach Exit | 2018-08-13 08:00 | 2018-08-17 16:00 | 5 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019663 | modified
Bocholtz Entry | 2018-08-13 08:00 | 2018-08-18 06:00 | 5 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019663 | terminated
Wallbach Exit | 2018-08-13 08:00 | 2018-08-18 06:00 | 5 | 2.975.096* kWh/h 19,4% | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21019663 | terminated | *of which: FAC = 2.727.202 kWh/h RAC = 247.894 kWh/h
Wallbach Exit | 2018-08-30 09:00 | 2018-08-30 14:00 | 1 | 2.409.689 kWh/h (15,7%) | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020295 | terminated
Wallbach Exit | 2018-10-01 06:00 | 2019-01-01 06:00 | 93 | 6.617.379* kWh/h 43,3 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FAC = 1.522.591 kWh/h RAC = 5.094.788 kWh/h
Bocholtz Entry | 2018-10-01 06:00 | 2019-01-01 06:00 | 93 | 2.327.983* kWh/h 15,2% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: cFAC = 1.868.595 kWh/h RAC = 459.388 kWh/h
Wallbach Exit | 2019-01-01 06:00 | 2019-04-01 06:00 | 91 | 5.916.154* kWh/h 38,7 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FAC = 821.366 kWh/h RAC = 5.094.788 kWh/h
Bocholtz Entry | 2019-01-01 06:00 | 2019-04-01 06:00 | 91 | 2.314.729* kWh/h 15,1% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit and Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: cFAC = 1.977.416 kWh/h RAC = 337.313 kWh/h
Bocholtz Entry | 2019-01-01 06:00 | 2019-04-01 06:00 | 91 | 2.314.729* kWh/h 15,1% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit and Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: cFAC = 1.977.416 kWh/h RAC = 337.313 kWh/h
Wallbach Exit | 2019-04-01 06:00 | 2019-10-01 06:00 | 184 | 6.038.229* kWh/h 39,5 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FAC = 943.441 kWh/h RAC = 5.094.788 kWh/h
Bocholtz Entry | 2019-04-01 06:00 | 2019-10-01 06:00 | 184 | 2.749.701* kWh/h 18% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: cFAC = 1.977.416 kWh/h RAC = 772.285 kWh/h
Bocholtz Entry | 2019-04-01 06:00 | 2019-10-01 06:00 | 184 | 2.749.701* kWh/h 18% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: cFAC = 1.977.416 kWh/h RAC = 772.285 kWh/h
Wallbach Exit | 2019-10-01 06:00 | 2020-01-01 06:00 | 93 | 6.266.154* kWh/h 41 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FAC = 1.171.366 kWh/h RAC = 5.094.788 kWh/h
Bocholtz Entry | 2019-10-01 06:00 | 2020-01-01 06:00 | 93 | 2.314.728* kWh/h 15,1% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: cFAC = 1.977.416 kWh/h RAC = 337.312 kWh/h
Bocholtz Entry | 2019-10-01 06:00 | 2020-01-01 06:00 | 93 | 2.314.728* kWh/h 15,1% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: cFAC = 1.977.416 kWh/h RAC = 337.312 kWh/h
Wallbach Exit | 2020-01-01 06:00 | 2020-04-01 06:00 | 92 | 6.285.848* kWh/h 41 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FAC = 1.191.060 kWh/h RAC = 5.094.788 kWh/h
Bocholtz Entry | 2020-01-01 06:00 | 2020-04-01 06:00 | 92 | 2.314.728* kWh/h 15,1% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: cFAC = 1.488.769 kWh/h RAC = 825.959 kWh/h
Bocholtz Entry | 2020-01-01 06:00 | 2020-04-01 06:00 | 92 | 2.314.728* kWh/h 15,1% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: cFAC = 1.488.769 kWh/h RAC = 825.959 kWh/h
Wallbach Exit | 2020-04-01 06:00 | 2020-10-01 06:00 | 184 | 6.399.543* kWh/h 41,8 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FAC = 1.304.755 kWh/h RAC = 5.094.788 kWh/h
Bocholtz Entry | 2020-04-01 06:00 | 2020-10-01 06:00 | 184 | 2.397.204* kWh/h 15,7% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: cFAC = 1.488.769 kWh/h RAC = 908.435 kWh/h
Bocholtz Entry | 2020-04-01 06:00 | 2020-10-01 06:00 | 184 | 2.397.204* kWh/h 15,7% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: cFAC = 1.488.769 kWh/h RAC = 908.435 kWh/h