## Maintenances
Last Update: 01/10/2019 15:14:04
Affected Point | Start | End | Duration (Days) | Reduction of the TAC due to the maintenance | possible impact on firm bookings | Work | Affected pipeline or network | Work No. | Status | Additional information
Wallbach Exit | 2019-01-01 06:00 | 2019-04-01 06:00 | 90 | 5.916.154* kWh/h 38,7 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: FZK = 821.366 kWh/h BZK = 5.094.788 kWh/h
Bocholtz Entry | 2019-01-01 06:00 | 2019-04-01 06:00 | 90 | 2.314.729* kWh/h 15,1% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit and Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: bFZK = 1.977.416 kWh/h BZK = 337.313 kWh/h
Bocholtz Entry | 2019-01-01 06:00 | 2019-04-01 06:00 | 90 | 2.314.729* kWh/h 15,1% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit and Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: bFZK = 1.977.416 kWh/h BZK = 337.313 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2019-04-01 06:00 | 2019-10-01 06:00 | 183 | 6.038.229* kWh/h 39,5 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: FZK = 943.441 kWh/h BZK = 5.094.788 kWh/h
Bocholtz Entry | 2019-04-01 06:00 | 2019-10-01 06:00 | 183 | 2.749.701* kWh/h 18% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: bFZK = 1.977.416 kWh/h BZK = 772.285 kWh/h
Bocholtz Entry | 2019-04-01 06:00 | 2019-10-01 06:00 | 183 | 2.749.701* kWh/h 18% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | terminated | *of which: bFZK = 1.977.416 kWh/h BZK = 772.285 kWh/h
Bocholtz Entry | 2019-04-01 06:00 | 2019-04-13 06:00 | 12 | 1.458.632* kWh/h 9,5 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020872 | terminated | *of which: bFZK = 1.458.632 kWh/h
Wallbach Exit | 2019-04-01 06:00 | 2019-04-13 06:00 | 12 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020872 | terminated
Bocholtz Entry | 2019-04-09 06:00 | 2019-04-11 06:00 | 2 | 5.731.139* kWh/h 37,5 % | yes | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | modified | *of which: bFZK = 4.063.952 kWh/h FZK = 1.667.187 kWh/h
Wallbach Exit | 2019-04-09 06:00 | 2019-04-11 06:00 | 2 | - | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | modified
Bocholtz Exit | 2019-04-09 06:00 | 2019-04-11 06:00 | 2 | 3.454.000 kWh/h 100 % | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | modified
Wallbach Entry | 2019-04-09 06:00 | 2019-04-11 06:00 | 2 | 3.454.000 kWh/h 50,4 % | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | modified
Bocholtz Entry | 2019-04-09 06:00 | 2019-04-12 06:00 | 3 | 5.731.139* kWh/h 37,5 % | yes | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | terminated | *of which: bFZK = 4.063.952 kWh/h FZK = 1.667.187 kWh/h
Wallbach Exit | 2019-04-09 06:00 | 2019-04-12 06:00 | 3 | - | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | terminated
Bocholtz Exit | 2019-04-09 06:00 | 2019-04-12 06:00 | 3 | 3.454.000 kWh/h 100 % | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | terminated
Wallbach Entry | 2019-04-09 06:00 | 2019-04-12 06:00 | 3 | 3.454.000 kWh/h 50,4 % | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020874 | terminated
Bocholtz Entry | 2019-04-23 06:00 | 2019-05-06 06:00 | 13 | 1.783.766 kWh/h 11,7 % | no | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020884 | terminated
Wallbach Exit | 2019-04-23 06:00 | 2019-05-06 06:00 | 13 | - | no | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020884 | terminated
Bocholtz Entry | 2019-05-06 06:00 | 2019-06-08 06:00 | 33 | 5.444.738* kWh/h 35,6 % | yes | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | TENP Pipeline | 21020875 | terminated | *of which: bFZK = 5.040.983 kWh/h FZK = 403.755 kWh/h
Wallbach Exit | 2019-05-06 06:00 | 2019-06-08 06:00 | 33 | 7.361.771* kWh/h 48,1 % | yes | Planned maintenance works in a gas pressure regulating and metering station could impact capacities at affected entries/exits | TENP Pipeline | 21020875 | terminated | *FZK
Wallbach Exit | 2019-06-03 06:00 | 2019-06-08 06:00 | 5 | 7.611.771* kWh/h 49,8 % | yes | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020876 | modified | *FZK
Wallbach Exit | 2019-06-03 06:00 | 2019-06-08 06:00 | 5 | - | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020876 | terminated
Wallbach Entry | 2019-06-03 06:00 | 2019-06-08 06:00 | 5 | 5.155.212 kWh/h 75,3% | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21020876 | terminated
Bocholtz Entry | 2019-06-10 06:00 | 2019-09-21 06:00 | 103 | nein | no | Planned maintenance works could impact capacities at affected entries/exits | TENP Pipeline | 21021165 | terminated
Bocholtz Entry | 2019-06-23 06:00 | 2019-06-29 06:00 | 6 | 2.094.990* kWh/h 13,7 % | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020877 | modified | *bFZK
Bocholtz Entry | 2019-06-23 06:00 | 2019-06-29 06:00 | 6 | 2.865.990* kWh/h 18,7 % | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020877 | terminated | *bFZK
Bocholtz Entry | 2019-06-24 06:00 | 2019-07-06 06:00 | 12 | no indication | currently not foreseeable | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020885 | postponed | Postponed to 29/07/2019 06:00 - 11/08/2019 06:00
IP Wallbach Exit & VIP Germany-CH Exit | 2019-06-24 06:00 | 2019-07-06 06:00 | 12 | no indication | currently not foreseeable | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020885 | postponed | Postponed to 29/07/2019 06:00 - 11/08/2019 06:00
Bocholtz Entry | 2019-07-29 06:00 | 2019-08-11 06:00 | 13 | no indication | currently not foreseeable | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020885 | modified
IP Wallbach Exit & VIP Germany-CH Exit | 2019-07-29 06:00 | 2019-08-11 06:00 | 13 | no indication | currently not foreseeable | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020885 | modified
Bocholtz Entry | 2019-07-29 06:00 | 2019-08-11 06:00 | 13 | - | no | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020885 | terminated
IP Wallbach Exit & VIP Germany-CH Exit | 2019-07-29 06:00 | 2019-08-11 06:00 | 13 | - | no | Planned maintenance works could impact capacities at affected entries/exits | OGE-Network | 21020885 | terminated
Bocholtz Entry | 2019-09-02 06:00 | 2019-09-07 06:00 | 5 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020878 | terminated
IP Wallbach Exit & VIP Germany-CH Exit | 2019-09-02 06:00 | 2019-09-07 06:00 | 5 | 2.607.014* kWh/h 17 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020878 | modified | *FZK
Bocholtz Entry | 2019-09-02 06:00 | 2019-09-07 06:00 | 5 | 1.457.753* kWh/h 9,5 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020879 | modified | *bFZK
Bocholtz Entry | 2019-09-02 06:00 | 2019-09-07 06:00 | 5 | 1.457.753* kWh/h 9,5 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020879 | terminated | *of which: bFZK 1.453.998 kWh/h FZK 3.755 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2019-09-02 06:00 | 2019-09-03 06:00 | 1 | 2.607.014* kWh/h 17 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020878 | terminated | *FZK
Bocholtz Entry | 2019-09-03 06:00 | 2019-09-06 06:00 | 3 | 1.457.753* kWh/h 9,5 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020879 | modified | *bFZK
Bocholtz Entry | 2019-09-03 06:00 | 2019-09-06 06:00 | 3 | 2.164.503* kWh/h 14,1 % | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020879 | modified | *bFZK
IP Wallbach Exit & VIP Germany-CH Exit | 2019-09-03 06:00 | 2019-09-06 06:00 | 3 | 2.542.764* kWh/h 16,6 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020879 | terminated | *FZK
Bocholtz Entry | 2019-09-03 06:00 | 2019-09-06 06:00 | 3 | 706.750* kWh/h 4,6% | yes | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020879 | terminated | *bFZK
IP Wallbach Exit & VIP Germany-CH Exit | 2019-09-06 06:00 | 2019-09-07 06:00 | 1 | 2.607.014* kWh/h 17 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020878 | terminated | *FZK
Bocholtz Entry | 2019-09-09 06:00 | 2019-09-14 06:00 | 5 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020880 | terminated
IP Wallbach Exit & VIP Germany-CH Exit | 2019-09-09 06:00 | 2019-09-14 06:00 | 5 | 2.607.014* kWh/h 17 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020880 | terminated | *FZK
Bocholtz Entry | 2019-09-10 06:00 | 2019-09-13 06:00 | 3 | - | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020881 | terminated
IP Wallbach Exit & VIP Germany-CH Exit | 2019-09-10 06:00 | 2019-09-13 06:00 | 3 | 3.821.339* kWh/h 25 % | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020881 | modified | *FZK
IP Wallbach Exit & VIP Germany-CH Exit | 2019-09-10 06:00 | 2019-09-13 06:00 | 3 | 1.214.325* kWh/h 7,9% | no | Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | 21020881 | terminated | *FZK
IP Wallbach Exit & VIP Germany-CH Exit | 2019-10-01 06:00 | 2020-01-01 06:00 | 92 | 6.266.154* kWh/h 41 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FZK = 1.171.366 kWh/h BZK = 5.094.788 kWh/h
Bocholtz Entry | 2019-10-01 06:00 | 2020-01-01 06:00 | 92 | 2.314.728* kWh/h 15,1% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: bFZK = 1.977.416 kWh/h BZK = 337.312 kWh/h
Bocholtz Entry | 2019-10-01 06:00 | 2020-01-01 06:00 | 92 | 2.314.728* kWh/h 15,1% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: bFZK = 1.977.416 kWh/h BZK = 337.312 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 6.285.848* kWh/h 41 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FZK = 1.191.060 kWh/h BZK = 5.094.788 kWh/h
Bocholtz Entry | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 2.314.728* kWh/h 15,1% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: bFZK = 1.488.769 kWh/h BZK = 825.959 kWh/h
Bocholtz Entry | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 2.314.728* kWh/h 15,1% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: bFZK = 1.488.769 kWh/h BZK = 825.959 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-04-01 06:00 | 2020-10-01 06:00 | 183 | 6.399.543* kWh/h 41,8 % | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | 21019101 | active | *of which: FZK = 1.304.755 kWh/h BZK = 5.094.788 kWh/h
Bocholtz Entry | 2020-04-01 06:00 | 2020-10-01 06:00 | 183 | 2.397.204* kWh/h 15,7% | yes | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | modified | *of which: bFZK = 1.488.769 kWh/h BZK = 908.435 kWh/h
Bocholtz Entry | 2020-04-01 06:00 | 2020-10-01 06:00 | 183 | 2.397.204* kWh/h 15,7% | no | Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Bocholtz Entry may be impacted. | TENP Pipeline | 21019101 | active | *of which: bFZK = 1.488.769 kWh/h BZK = 908.435 kWh/h