## Maintenances
Last Update: 30/04/2020 08:36:55
Affected Point | Start | End | Duration (Days) | Commercial Capacity without maintenances | Reduction due to the maintenance | possible impact on firm bookings | Work | Affected pipeline or network | Status | Additional information
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 7.704.063 kWh/h | 2.314.728 kWh/h* (30,0%) | yes | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | modified | *of which: FZK = 0 kWh/h bFZK = 1.488.769 kWh/h DZK = 825.959 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 7.704.063 kWh/h | 2.314.728 kWh/h* (30,0%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | modified | *of which: FZK = 0 kWh/h bFZK = 1.488.769 kWh/h DZK = 825.959 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 7.704.063 kWh/h | 2.519.939 kWh/h* (32,7%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | canceled | *of which: FZK = 0 kWh/h bFZK = 1.488.769 kWh/h DZK = 1.031.170 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-04-01 06:00 | 2020-10-01 06:00 | 183 | 7.704.063 kWh/h | 2.397.204 kWh/h* (31,1%) | yes | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | modified | *of which: FZK = 0 kWh/h bFZK = 1.488.769 kWh/h DZK = 908.435 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-04-01 06:00 | 2020-10-01 06:00 | 183 | 7.704.063 kWh/h | 2.397.204 kWh/h* (31,1%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | modified | *of which: FZK = 0 kWh/h bFZK = 1.488.769 kWh/h DZK = 908.435 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-04-01 06:00 | 2020-08-01 06:00 | 122 | 7.704.063 kWh/h | 7.187.100 kWh/h* (93,3%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 0 kWh/h bFZK = 5.947.312 kWh/h DZK = 1.239.788 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 01/04/2020 06:00:00 Maintenance postponed to the year 2021 | 01/08/2020 06:00:00 Maintenance postponed to the year 2021 | 122 | 7.704.063 kWh/h | 398.331 kWh/h* (5,2%) | no | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | postponed | *of which: FZK = 0 kWh/h bFZK = 4.458.543 kWh/h DZK = -4.060.212 kWh/h - Due to this maintenance, Fluxys TENP has to reduce bFZK-capacity, but can offer DZK-capacity instead.
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-08-01 06:00 | 2020-10-01 06:00 | 61 | 7.704.063 kWh/h | 2.602.415 kWh/h* (33,8%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | canceled | *of which: FZK = 0 kWh/h bFZK = 1.488.769 kWh/h DZK = 1.113.646 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-08-03 06:00 | 2020-10-01 06:00 | 59 | 7.704.063 kWh/h | 2.390.901 kWh/h* (31,0%) | no | 210221951: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 0 kWh/h bFZK = 2.390.901 kWh/h DZK = 0 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-08-03 06:00 | 2020-08-08 06:00 | 5 | 7.704.063 kWh/h | 7.704.063 kWh/h* (100,0%) | yes | 21022211: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 2.096.245 kWh/h bFZK = 4.824.356 kWh/h DZK = 783.462 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-08-10 06:00 | 2020-08-26 06:00 | 16 | 7.704.063 kWh/h | 5.311.063 kWh/h* (68,9%) | yes | 21022456: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 232.277 kWh/h bFZK = 4.824.356 kWh/h DZK = 254.430 kWh/h
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2020-10-01 06:00 | 2021-01-01 06:00 | 92 | 7.704.063 kWh/h | 1.571.245 kWh/h* (20,4%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | canceled | *of which: FZK = 0 kWh/h bFZK = 1.488.769 kWh/h DZK = 82.476 kWh/h
IP Bocholtz Exit & VIP TTF-NCG-H Exit | 2020-08-03 06:00 | 2020-08-08 06:00 | 5 | 3.454.000 kWh/h | 3.454.000 kWh/h* (100,0%) | no | 21022211: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 0 kWh/h DZK = 3.454.000 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 9.692.402 kWh/h | 6.285.848 kWh/h* (64,9%) | no | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 1.191.060 kWh/h DZK = 5.094.788 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-01-01 06:00 | 2020-04-01 06:00 | 91 | 9.692.402 kWh/h | 5.935.848 kWh/h* (61,2%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | canceled | *of which: FZK = 841.060 kWh/h DZK = 5.094.788 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-04-01 06:00 | 2020-10-01 06:00 | 183 | 9.692.402 kWh/h | 6.399.543 kWh/h* (66,0%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | canceled | *of which: FZK = 1.304.755 kWh/h DZK = 5.094.788 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-04-01 06:00 | 2020-08-01 06:00 | 122 | 9.692.402 kWh/h | 7.292.644 kWh/h* (75,2%) | yes | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 6.052.856 kWh/h DZK = 1.239.788 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 01/04/2020 06:00:00 Maintenance postponed to the year 2021 | 01/08/2020 06:00:00 Maintenance postponed to the year 2021 | 122 | 9.692.402 kWh/h | 901.584 kWh/h* (9,3%) | yes | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | postponed | *of which: FZK = 4.961.796 kWh/h DZK = -4.060.212 kWh/h - Due to this maintenance, Fluxys TENP has to reduce FZK-capacity, but can offer DZK-capacity instead.
IP Wallbach Exit & VIP Germany-CH Exit | 2020-08-01 06:00 | 2020-10-01 06:00 | 61 | 9.692.402 kWh/h | 6.049.543 kWh/h* (62,4%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | canceled | *of which: FZK = 954.755 kWh/h DZK = 5.094.788 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-08-03 06:00 | 2020-10-01 06:00 | 59 | 9.692.402 kWh/h | no indication | no | 210221951: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | no indication
IP Wallbach Exit & VIP Germany-CH Exit | 2020-08-03 06:00 | 2020-08-08 06:00 | 5 | 9.692.402 kWh/h | 2.989.552 kWh/h* (30,8%) | no | 21022221: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 2.206.090 kWh/h DZK = 783.462 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-08-10 06:00 | 2020-08-15 06:00 | 5 | 9.692.402 kWh/h | 2.086.840 kWh/h* (21,5%) | no | 21022456 + 21022220: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 2.341.270 kWh/h DZK = -254.430 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-08-10 06:00 | 2020-08-26 06:00 | 16 | 9.692.402 kWh/h | 254.430 kWh/h* (2,6%) | no | 21022456: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 0 kWh/h DZK = 254.430 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-08-10 06:00 | 2020-08-15 06:00 | 5 | 9.692.402 kWh/h | 2.595.700 kWh/h* (26,8%) | no | 21022456 + 21022220: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 2.341.270 kWh/h DZK = 254.430 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2020-10-01 06:00 | 2021-01-01 06:00 | 92 | 9.692.402 kWh/h | 6.285.848 kWh/h* (64,9%) | no | 21019101: Due to ongoing, additional inspections on the TENP pipeline and the measures derived out of these inspections, transport capacities of Fluxys TENP at the IP Wallbach Exit may be impacted. | TENP Pipeline | canceled | *of which: FZK = 1.191.060 kWh/h DZK = 5.094.788 kWh/h
VIP Belgium-NCG Entry | 2020-04-01 06:00 | 2020-08-01 06:00 | 122 | 1.590.630 kWh/h | 1.186.875 kWh/h* (74,6%) | no | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 0 kWh/h bFZK = 1.186.875 kWh/h DZK = 0 kWh/h
VIP Belgium-NCG Entry | 2020-04-01 06:00 | 2020-08-01 06:00 | 122 | 1.590.630 kWh/h | 1.590.630 kWh/h* (100,0%) | no | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 403.755 kWh/h bFZK = 1.186.875 kWh/h DZK = 0 kWh/h
VIP Belgium-NCG Entry | 01/04/2020 06:00:00 Maintenance postponed to the year 2021 | 01/08/2020 06:00:00 Maintenance postponed to the year 2021 | 122 | 1.590.630 kWh/h | 1.186.875 kWh/h* (74,6%) | no | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | postponed | *of which: FZK = 0 kWh/h bFZK = 1.186.875 kWh/h DZK = 0 kWh/h
VIP Belgium-NCG Exit | 01/04/2020 06:00:00 Maintenance postponed to the year 2021 | 01/08/2020 06:00:00 Maintenance postponed to the year 2021 | 122 | 3.396.000 kWh/h | 3.396.000 kWh/h* (100,0%) | no | 21021949: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | postponed | *of which: FZK = 0 kWh/h DZK = 3.396.000 kWh/h