## Maintenances
Last Update: 09/07/2020 11:48:25
Affected Point | Start | End | Duration (Days) | Commercial Capacity without maintenances | Reduction due to the maintenance | possible impact on firm bookings | Work | Affected pipeline or network | Status | Additional information
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2021-04-01 06:00 | 2021-07-01 06:00 | 91 | 9.532.701 kWh/h | 3.950.006 kWh/h* (41,4%) | no | 21022876: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 0 kWh/h bFZK = 7.098.256 kWh/h DZK = -3.148.250 kWh/h - Start of the maintenance brought forward from 6 April to 1 April. Due to this maintenance, Fluxys TENP has to reduce bFZK-capacity, but can offer DZK-capacity instead.
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2021-04-06 06:00 | 2021-07-01 06:00 | 86 | 9.532.701 kWh/h | 3.950.006 kWh/h* (41,4%) | no | 21022876: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 0 kWh/h bFZK = 7.098.256 kWh/h DZK = -3.148.250 kWh/h - Due to this maintenance, Fluxys TENP has to reduce bFZK-capacity, but can offer DZK-capacity instead.
IP Bocholtz Entry & VIP TTF-NCG-H Entry | 2021-07-01 06:00 | 2021-10-01 06:00 | 92 | 9.532.701 kWh/h | 3.688.778 kWh/h* (38,7%) | no | 21022877: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 0 kWh/h bFZK = 3.688.778 kWh/h DZK = 0 kWh/h
IP Wallbach Exit & VIP Germany-CH Exit | 2021-04-01 06:00 | 2021-05-01 06:00 | 30 | 9.952.613 kWh/h | 2.514.573 kWh/h* (25,3%) | yes | 21022876: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 5.652.520 kWh/h DZK = -3.137.947 kWh/h - Start of the maintenance brought forward from 6 April to 1 April. Due to this maintenance, Fluxys TENP has to reduce FZK-capacity, but can offer DZK-capacity instead.
IP Wallbach Exit & VIP Germany-CH Exit | 2021-04-06 06:00 | 2021-05-01 06:00 | 25 | 9.952.613 kWh/h | 2.514.573 kWh/h* (25,3%) | yes | 21022876: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | modified | *of which: FZK = 5.652.520 kWh/h DZK = -3.137.947 kWh/h - Due to this maintenance, Fluxys TENP has to reduce FZK-capacity, but can offer DZK-capacity instead.
IP Wallbach Exit & VIP Germany-CH Exit | 2021-05-01 06:00 | 2021-06-01 06:00 | 31 | 9.952.613 kWh/h | 2.490.829 kWh/h* (25,0%) | yes | 21022876: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 5.660.648 kWh/h DZK = -3.169.819 kWh/h - Due to this maintenance, Fluxys TENP has to reduce FZK-capacity, but can offer DZK-capacity instead.
IP Wallbach Exit & VIP Germany-CH Exit | 2021-06-01 06:00 | 2021-07-01 06:00 | 30 | 9.952.613 kWh/h | 2.481.067 kWh/h* (24,9%) | yes | 21022876: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 5.663.267 kWh/h DZK = -3.182.200 kWh/h - Due to this maintenance, Fluxys TENP has to reduce FZK-capacity, but can offer DZK-capacity instead.
IP Wallbach Exit & VIP Germany-CH Exit | 2021-07-01 06:00 | 2021-10-01 06:00 | 92 | 9.952.613 kWh/h | 1.040.850 kWh/h* (10,5%) | no | 21022877: Planned maintenance works in a compressor station could impact capacities at affected entries/exits | TENP Pipeline | active | *of which: FZK = 1.040.850 kWh/h DZK = 0 kWh/h